## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-SWEN-261-600-D-Myriad Desserts
Testing Team Name | 2221-SWEN-261-600-C-Phoenixes

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a user I want to see a list of products so that I choose what to purchase. | Given that I am see the dashboard when I click the User tab then I can see list of products. | Pass | MM; 23/10/22 | Pass | GC;15/11/22
| Given that I see a list of products when I select a product then I can see details of the product. | Pass | MM; 23/10/22 | Pass | SC;15/11/22
As an Employee, I want to see a list of inventory items so that I can select an item. | Given that I see a list of items when I select an item then I can see details of the item. | Pass | AK; 26/10/22 | Pass | MM;15/11/22
As an Employee, I want to add an inventory item so that it is included in the list of inventory items. | Given that I add in the necessary details when I click Add then I expect the new item to show in the inventory list | Pass | AB; 26/10/22 | Pass | AB;15/11/22
As an Employee, I want to edit an inventory item so that the changes are made and shown in the inventory. | Given that I edit certain values for the item when I click done then I expect the changes to be shown for the item. | Pass | ST; 28/10/22 | Pass | AK;15/11/22
As an Employee, I want to delete an inventory item so that it is no longer is visible on the inventory list. | Given that I enter the ID of the product I want to delete when I click Delete then I expect the item to no longer show on the inventory list. | Pass | AK; 26/10/22 | Pass | GC;15/11/22
As an Employee, I want to get notifications on products that are running low on stock so that I can restock them. | Given the quantity of a product reaches zero, when the quantity gets updated then I expect to receive the reorder notification. | Pass | GC; 3/11/22 | Pass | AB;15/11/22
As a Customer, I want to create an account so that I can order products. | Given that I am not yet a registered customer when I see a Sign up option then I must be able to create an account. |  |  | Pass | MM; 15/11/22
As a Customer, I want to login with my account so I can see the list of products | Given that I am a registered customer when I see the Login Option then I must be able to login. |  |  | Pass | AB;15/11/22
| Given that I am not yet a registered customer when I enter the credentials and click on Login then I must be able to see Login failed message. |  |  | Pass | AK; 15/11/22
| Given that I am not yet a registered customer when I see the login page then I must be able to see a Signup option on the login page. |  |  | Pass | MM; 15/11/22
| Given that the user has entered their credentials when they click Login, they should be redirected to Dashboard. |  |  | Pass | AB; 15/11/22
As a Employee, I want to login into the admin account so that I can perform inventory management | Given that I have not signed in when I see a Login option then I must be able to login using admin credentials. |  |  | Pass | AK; 15/11/22
| Given that I have entered the admin credentials when I click on Login then I must be able to see the list of inventory items. |  |  | Pass | GC; 15/11/22
As a customer, I want to be able to choose products to be in the cart in order to purchase them. | Given that I see a product I like when I select to add this product to the cart then I expect a notification to pop up saying the an item is added to the cart. |  |  | Pass | SC; 17/11/22
| Given that I have clicked on add to cart when I click on the shopping cart icon then I expect to be redirected to the shopping cart page |  |  | Pass | AB; 17/11/22
| Given that I have clicked on shopping cart icon when I am redirected to the shopping cart page then I expect to see the item I selected in the cart. |  |  | Pass | AK; 17/11/22
As a customer, I want to edit the shopping cart so I can make changes in my order preferences. | Given that I see the option to delete button for a specific item when I click on the delete button then I expect to see the item be removed from the cart. |  |  | Pass | MM; 18/11/22
| Given that I see the option to input quantity for a item in the cart when I enter a number then I expect the quantity for a specific item to be updated. |  |  | Pass | GC; 18/11/22
| Given that I am in the shopping cart and I see the go Back option when I click on the Go Back button then I expect the items on the cart to stay and I be redirected to the products page |  |  | Pass | SC; 18/11/22
| Given that I see a clear cart button when I click this button then I expect all items in the cart to be cleared. |  |  | Pass | AB; 18/11/22
As a Customer I want to be able to edit the ingredients so that I can make a customized product. | Given that I see the customize button when I click on it then I expect to see a list of available ingredients that I use to customize the product |  |  | Pass | SC; 19/11/22
| Given that I want to add ingredients to my selected product when I click on select button for a specific ingredient then I must see the product is customized with this ingredient in the shopping cart. |  |  | Pass | GC; 19/11/22
| Given that I want to remove ingredients to my selected product when I click on deselect button for a specific ingredient then I must see the product is not customized with this ingredient in the shopping cart. |  |  | Pass | MM; 19/11/22
As a customer, I want to finalize my preferences shown on the shopping cart so I can confirm my order. | Given that I see the option of preview checkout on the shopping cart, when I click it, I expect that the total price of items in the cart to show |  |  | Pass | AK; 19/11/22
| Given that I see the option of checkout on the shopping cart, when I click it, I expect that my most recent changes are saved |  |  | Pass | AB; 19/11/22
| Given that I see the option of checkout on the shopping cart, when I click it, I expect a notification that says cart is checked out. |  |  | Pass | GC; 19/11/22
| Given that I see the option of checkout on the shopping cart, when I click it, I expect that all items in the shopping cart are cleared. |  |  | Pass | SC; 20/11/22
Key Legend
indicates User Story is not ready for testing.